## Overview
How might we redesign the 'approach' & 'triage/ advice' stages of the customer's journey to better meet the needs of customers and staff?
Discovery Goals
- Establish a detailed understanding of how the front door to the homelessness service currently works
- Put together a detailed picture of the experience 1. staff have working in the front door and 2. customers have engaging with the service through the front door
- Pick out key insights such as specific parts of the process that don’t work well or specific opportunities for change
- Put together a picture of the user journey, including when they become aware of the service (i.e. before they have approached)
- Get a detailed understanding of the types of people that use the front door and the types of problems they have
User Groups
Customer
Customer Service Officer
Homelessness/ Housing Advice Officer
Advocate
Internal Team Officer (Middlesbrough)
Internal Team Officer (13)
Partner Agency Officer
Discovery Guidelines
- All user research will be totally anonymous
- Document everything in the team sharepoint
- Always best to debrief straight after interviews/ workshops and capture immediate learnings/ insights
- During interviews or workshops capture important quotes directly
- Frame questions in an open way. Open with some general questions, then go deep
What we already know
- Some customers contacting out of hours and receiving different response to officer hours
- Lots of missed appointments when using appointment-based system
- Incorrect perceptions from partners around what service does and what it can offer
Assumptions
- There is not a huge amount of understanding about what the service provides and that more approaches could be prevented
- Good amount of initial approaches at the moment could be dealt earlier with signposting or right advice and information
Where we need to learn more/ what we don't know
- Would be good to understand experience of past, current and future service users​
- Are we providing relevant tools at pre-approach stage?
- Is the journey to an assessment streamlined?​
- Would be good to measure and understand amount of contact that is unnecessary
- For data work it would be good to pick up if there is something we are not recording​

## User Research Logistics
Name | Team | Role | Interviewer | Date | Time | Complete? | Logistic notes

## Homelessness Forum Survey
Middlesbrough Front Door Redesign Project - Stakeholder Survey
Thirteen’s Homeless & Housing Advice team are looking to improve the experience of people seeking help and advice from the service. We want to better understand people’s current experiences of accessing and approaching the service both at Rivers House and other channels available (like online or over the phone). We’d like to hear about your experiences - whether that be supporting your clients and service users, making referrals or contacting us directly. This survey is going to all members of the Middlesbrough Homelessness Forum so not all questions will be relevant. Please leave any questions where this is the case. The survey should take no more than 10 - 15 minutes to complete and your response is much appreciated. If you have any questions about the survey, please contact <>.
Organisation Information
Organisation Name Organisation Type
1. Prior knowledge and expectations
Q1. | How would you rate your knowledge of the support on offer from the homeless service? Very Good Good Not Good None | Question on expectations? Channels used?
Q2. | Do you direct people to the service for support? Yes No
| Q3. If yes to Q.2, | Does this knowledge affect your decision to direct people to the service? Yes No Please explain your answer [free text]
2. Referrals to the service
Q4. | When do you direct people to the service for support? [Select multiple] As soon as we identify a housing or homelessness issue When they meet the legal definitions of 'homeless' or 'threatened with homelessness' in 56 days When we can no longer support them When we think they meet certain criteria for enhanced help and support Other [please specify]
Q5. | Do you offer to contact the service on their behalf? Yes No Depends [please explain]
Q6. | Do you offer to visit with them? Yes No Depends [please explain]
Q7. | Do you provide them with advice about their housing issue before directing them to us? Yes No
Q8. | If yes to Q.7, | [Please briefly outline the advice and support you would typically provide]
Q.9 | Do you continue to work with them after directing them to us? Yes No Depends [please explain]
3. First contact with the homeless service
Q.10 | The following statements are about your organisation's (bold) initial contacts with the homeless service about a client or issue. Based on your typical experience (bold), how much do you agree or disagree with the following statements… We are able to access the service using a channel and time that suits us We can explain our reason for contacting and make ourselves understood We are treated with respect and courtesy There is a clear outcome at the end of the initial contact I know what I need to do next (if anything) We are happy with the outcome of the initial contact Information we provide at the initial contact is not asked for again Strongly Agree Agree Neither Disagree Strongly Disagree
Q.11 | The following statements are about your clients' or service users' (bold) first contact with the homeless service. Based on your typical experience (bold), how much do you agree or disagree with the following statements… The opening times of the housing office suit them The environment in the waiting room is comfortable They are treated with respect when they first approach the housing office They can explain their situation confidentially at the housing office They are able to make themselves understood Strongly Agree Agree Neither Disagree Strongly Disagree
4. Referrals from the homeless service
Q.12 | Do you receive referrals from the homeless service? Yes No
Q.13 | If yes to Q.12, | How are these referrals made? [select multiple] Staff at the homeless service tell people to come to us Staff at the homeless service make contact with us and link people in
| If yes to Q.12, | Does the referral process work at the moment for your organisation? Yes No [Please explain]
5. Advice provided
Q.13 | How would you rate the quality of information and advice provided by the service against the following criteria Accessible Accurate Clear & Concise Practical Strongly Agree Agree Neither Disagree Strongly Disagree [Please feel free to explain your ratings]
Q.14 | Please select any gaps in our provision of advice and information: People's legal rights and entitlements What our service can offer The way the process works Things people can do to help themselves Local services available Advice on preventing homelessness Advice on relieving homelessness Advice tailored to specific groups
6. Your experience
Q.15 | Can you give me an example of a really positive case when you initially approached the service on behalf of a client? Why was it positive? What was the outcome?
Q.16 | Can you give me an example of a really negative case when you initially approached the service on behalf of a client? Why was it negative? What was the outcome?
Q.17 | What do you find most frustrating with the current process to access help from the service? Why?
Q.18 | What do you find most helpful with the current process to access help from the service? Why?

## Staff Group Discussions
Interviewee: | Customer Service Officer
Key Questions
Can you tell me a bit about the work you do?
What do you think your role is in housing? What happens to cases when they are passed to the housing needs service?
What do you find most frustrating at work? Why?
What are the typical types of housing-related cases that present
Can you give me an example of a really positive experience in your role? Why was it positive? What was the outcome?
Can you give me an example of a really negative experience in your role? Why was it negative? What was the outcome?
How do customers usually behave when they speak to you? Are they angry, upset, confused, driven to solve their problems, looking for solutions etc?
How do you feel when you are dealing with customers with housing issues? Do you feel confident? Do you have the resources and knowledge at your disposal to manage the case effectively?
Which part of your role takes the longest time with housing-related cases? Which part is the most challenging?
Which part of your role is the most important with housing-related cases? Which part of your role has the most significant impact on customers?
Do you think the roles and responsibilies of customer services and the housing needs service is clear and well understood amongst staff? What about amongst customers?
Interviewee: | Customer Service Team Leader/ Manager
Key Questions
Can you tell me a bit about the work you do?
What do you think your role is in housing? What do you see as a success factor in terms of the job you do?
What do you find most frustrating at work? Why?
What are the typical types of housing-related cases that present
Can you give me an example of a really positive housing case you have managed? Why was it positive? What was the outcome?
Can you give me an example of a really negative housing case you have managed? Why was it negative? What was the outcome?
With housing cases, which part of the process takes the longest time? Which part of the process is the most challenging?
With housing cases, which part of the process is the most important? Which part of the process has the most significant impact on customers?
Interviewee: | Housing Needs Officer & Housing Needs Team Leader
Key Questions
Can you tell me a bit about the work you do?
What do you find most frustrating with the current 'front door' to the service? Why?
Can you give me an example of a really positive case where the front door to the service worked? Why was it positive? What was the outcome?
Can you give me an example of a really negative case where the front door to the service didn't work? Why was it negative? What was the outcome?
Which part of the front door process is the most important for you? Which part of the front door process has the most significant impact on the customer?
Which part of the front door process takes the longest time? Which part of the front door process is the most challenging?
Do you think the roles and responsibilies of customer services and the housing needs service is clear and well understood amongst staff? What about amongst customers?
What do you need in advance of a scheduled appointment with a customer to deliver the best outcome for them and the service?
Interviewee: | Internal Service Officer e.g. allocations, ASB etc.
Key Questions
Can you tell me a bit about the work you do?
What do you think your role is in housing? What do you see as a success factor in terms of the job you do?
What are the typical types of housing-related cases you deal with
Can you give me an example of a really positive housing case you have managed? Why was it positive? What was the outcome?
Can you give me an example of a really negative housing case you have managed? Why was it negative? What was the outcome?
How do you feel when you are dealing with customers with housing issues? Do you feel confident? Do you have the resources and knowledge at your disposal to manage the case effectively?
Which part of your role takes the longest time with housing-related cases? Which part is the most challenging?
Which part of your role is the most important with housing-related cases? Which part of your role has the most significant impact on customers?
What do you find most frustrating with the current process to access help from the housing needs service? Why?
What do you find most helpful with the current process to access help from the housing needs service? Why?

## Data
Data points
Total contacts through the front door - broken down by contact type / channel / month / year
Breakdown of contacts by outcome e.g. NFA / Signposted / referred elsewhere / appointment booked/ general advice etc.
Breakdown of referrals from specific partners (including internal teams)
Breakdown of who is accessing the homelessness servie by demographic groups (age groups, gender, ethnicity); reason for approach; needs [H-CLIC]
Website performance data – number of visitors (unique and returning), most used links, most used outbound links, data on acquisition of website users (e.g. Social media, news, websites, organic search, direct referral etc. - we want to understand where people are coming from), exit pages. This can be exported from Google Analytics.
Any complaints, correspondence or compliments relating to the front door
Missed appointments
Success factors
Awareness of support ​ Accessibility of service​ Quality of advice​ Appropriate outcome of initial contacts inc. signposting and referrals to correct agencies​ Management of expectations​ Customer feedback/ experience​

## Partner Interviews
Interviewee: | External Officer e.g. Aspire, members of champions network
Key Questions
Can you tell me a bit about the work you do?
What do you think your role is in housing? What do you see as a success factor in terms of the job you do?
What do you find most frustrating at work? Why?
What are the typical types of housing-related cases that present
How do you feel when you are dealing with customers with housing issues? Do you feel confident? Do you have the resources and knowledge at your disposal to manage the case effectively?
Which part of your role takes the longest time with housing-related cases? Which part is the most challenging?
Which part of your role is the most important with housing-related cases? Which part of your role has the most significant impact on customers?
Can you give me an example of a really positive case when you referred someone to the Council that was homeless or threatened with homelessness? Why was it positive? What was the outcome?
Can you give me an example of a really negative case when you referred someone to the Council that was homeless or threatened with homelessness? Why was it negative? What was the outcome?
What do you find most frustrating with the current process to access help from the Council's housing needs service? Why?
What do you find most helpful with the current process to access help from the Council's housing needs service? Why?